## Design
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Skar Boy - EBPs, SBPs, Weapons | 2 - High | 1 - Required For Release | Omar | Ready For Approval
Ard Boy - EBPs, SBPs, Weapons | 2 - High | 1 - Required For Release | Omar | Ready For Approval
Ard Boy attach ranged weapon swapping | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Tyranid Scout Unit Design | 3 - Medium | 1 - Required For Release | All | Unstarted |  | We need to decide on a design for this unit then write up that design
Balancing Tau | 2 - High | 1 - Required For Release | All | Iterating On |  | This is blocking any upkeep
Finish initial rosta for Tyranids | 3 - Medium | 1 - Required For Release | All | Iterating On
Tau upkeep | 3 - Medium | 1 - Required For Release | All | Blocked | Balancing Tau
Sisters Faith Rework | 2 - High | 1 - Required For Release | All | Working On First Pass |  | Also make laud hailers require a holy icon
Armour Resistance Rework | 4 - Low | 2 - Desired For Release | All | Working On First Pass
Implementing armour modifier to more places | 4 - Low | 2 - Desired For Release | All | Blocked | Armour Resistance Rework
Mass / Knockback Rework | 4 - Low | 2 - Desired For Release | All | Unstarted
OM add in leman variant unit | 3 - Medium | 1 - Required For Release | Omar | Unstarted
OM Assault Chim T3 weapon upgrade to assault cannon | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Revisit current global abilities design | 4 - Low | 1 - Required For Release | All | Unstarted
Design for Tyranids global abilities | 4 - Low | 1 - Required For Release | All | Unstarted
Design for OM global abilities | 4 - Low | 1 - Required For Release | All | Unstarted
Design for Tau global abilities | 4 - Low | 1 - Required For Release | All | Unstarted
Decide how upkeep works in early game | 4 - Low | 1 - Required For Release | Omar | Unstarted |  | Do we want people to have a certain number of points / gens before we charge them?
Setup ability target filters for new armours | 1 - Urgent | 1 - Required For Release | Unassigned | Unstarted
Add piercings to abilities | 2 - High | 1 - Required For Release | Unassigned | Unstarted
Revisit BRV Design | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
BRV Faction | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
New (and multiplayer?) Campaign | 4 - Low | 3 - Post-Release | Unassigned | Unstarted
Tutorial/Demo level | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Revisit design for Alpha Legion subfaction | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Remove predator variants from machine pit | 3 - Medium | 1 - Required For Release | Unassigned | Blocked | Code system
Check if khorne zerks require more iteration | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Add havoc unit | 3 - Medium | 2 - Desired For Release | Omar | Ready For Approval
Iterate on Raven to make it a viable unit | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Ravage terror ability | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Pass on Talos | 3 - Medium | 1 - Required For Release | Ben | Unstarted | Souls Abil | Change cannibalize to ability, iterate on ranged weapon, pathing, check it's damage stats
Starting bike scavange ability rework | 3 - Medium | 1 - Required For Release | Omar | Unstarted | Scavange Abil
Look at rekindled rage global | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Soul Destruction Design | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted |  | Possibly do this as a zombie ability
Add the Incubus Combat squad | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Design a T3 ranged unit for DE | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Settle on dark reaper design | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Get rid of farseer variants | 3 - Medium | 1 - Required For Release | Ben | Done
Merge the eldar embolden abilities | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Cumulative squad cap for bonesingers | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Eldar holofields ability | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted | Energy System
Decide on wraithguard / wraithblade unit | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Harlequin kiss ability changed to timed not targeted | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Revisit warlock sub-commander abilities | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Fire prism weapon swap ability | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Change guard assassin to research not addons | 4 - Low | 1 - Required For Release | Ben | Unstarted
Decide on Cln Brom | 5 - Trivial | 2 - Desired For Release | Unassigned | Unstarted
Earthshaker ability rework | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Revert change adding second turret (keep it in files) | 4 - Low | 1 - Required For Release | Unassigned | Unstarted
Rework hellhound T3 ability | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Rework marauder bomba | 2 - High | 1 - Required For Release | Ben | Unstarted |  | Bomb ability reworked into the combat and chang these bombs via weapon upgrades
Remove spotter vision ability | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Rework and re-add secondary artillery abilty to a mixed use smoke | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Vulnerable dreadnoughts have different weapons | 4 - Low | 1 - Required For Release | Omar | Unstarted
Look into the 2 land raider variants and decide what to do with them | 4 - Low | 1 - Required For Release | Omar | Unstarted
Revisit scholars | 3 - Medium | 1 - Required For Release | Omar | Working On First Pass
Astra-telepathica ability rework | 2 - High | 1 - Required For Release | Omar | Ready For Approval
OM Techmarine weapons rework | 3 - Medium | 1 - Required For Release | Omar | Unstarted |  | Possibly use the Obliterator slave group thing to improve this?
Cleanup OM folders to remove unusued EBPs, SBPs, Weapons, Icons, etc. | 3 - Medium | 1 - Required For Release | Omar | Paused / On Hold
Revoke smoke UI effect for the rhino | 3 - Medium | 1 - Required For Release | Ben | Unstarted
OM Big buildings Y height needs to be higher to stop fliers going through it | 5 - Trivial | 2 - Desired For Release | Ben | Unstarted
OM resize inquisition watch building slightly | 5 - Trivial | 2 - Desired For Release | Ben | Unstarted |  | Compare it to size of assault chimera to make sure it's big enough
Cryptek path | 3 - Medium | 1 - Required For Release | Ben | Waiting For Iteration
Skorpekh destroyer | 3 - Medium | 1 - Required For Release | Ben | Waiting For Iteration
Nightbringer & Deceiver rework | 4 - Low | 1 - Required For Release | Ben | Paused / On Hold
Destroyer holofields from upgrade using morale system | 4 - Low | 2 - Desired For Release | Ben | Unstarted | Energy System
Reviable necron vehicles? | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Necron wargear revisit | 4 - Low | 2 - Desired For Release | Ben | Unstarted |  | All of them still needed? And apply their icons on his selection ui
Necron scout unit ability rework | 4 - Low | 2 - Desired For Release | Ben | Unstarted |  | Timed infiltration ability?
Tomb spyder artillery weapon | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted | New Model
Orks general teleport pass and put them into a table | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Add lootas | 3 - Medium | 1 - Required For Release | Omar | Unstarted |  | Possibly add a new building for this
Add ability for burna boy nob | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Add oil spill ability for OM | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Buildable Grot Tanks | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Squiggoth alternative weapons depends on what's garrisoned | 5 - Trivial | 2 - Desired For Release | Ben | Unstarted
Warboss and killa kan rampage abilities | 4 - Low | 1 - Required For Release | Ben | Unstarted
Stikkbombs reworked so that they are throwing grenades as a ranged weapon | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Revisit Bad Dok weird juice ability and remove knockback round | 3 - Medium | 1 - Required For Release | Ben | Unstarted |  | Probably rework via code
Revisit ascension angels | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted |  | Possibly make them summoned squad from living saint?
Pass on sisters vehicles | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Possibly add castagator? | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Blessed ammo upgrade applies new piercing type | 3 - Medium | 2 - Desired For Release | Unassigned | Unstarted | Holy Piercing
Add holy piercing variants | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
SM scout sniper ability rework | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Terminator force commander needs to remember what weapon he gets after possess | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Rework apothecary combat stims ability | 4 - Low | 2 - Desired For Release | Ben | Unstarted
SM Shotgun blast rewritten as a high explosive round | 4 - Low | 1 - Required For Release | Omar | Unstarted
Scout smoke grenade infiltrates scout | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Remove scout blind grenade | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Tau add some battlesuit related researches | 3 - Medium | 2 - Desired For Release | Unassigned | Unstarted
Possibly add riptide as mont'ka T4 alternative relic unit | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Hammerhead gunship move some HP into a new energy shield | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted | Energy System
Ethereal can spawn elite version of vespid and kroot | 5 - Trivial | 4 - If we have time | Unassigned | Unstarted
Tau clones inherit from their parents | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Tau Drone Harbinger spawn different drone types | 3 - Medium | 2 - Desired For Release | Unassigned | Unstarted
Reduce overlap between reclemator and tomb spyder | 4 - Low | 4 - If we have time | Unassigned | Unstarted |  | Possibly tomb spyder melee range res orb instead of harvest?
Take another look at Ork post T4 upgrades | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Rework mind war scaling | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Remove initial delay time from global abilities | 2 - High | 1 - Required For Release | All | Unstarted
Take another look at Tau population system | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Tau give Snapshot a wind up time | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted | Animation
Stop Stikkbombas smoke effect not stacking | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Move combat drones to Tier 1 buildable from barracks | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Move pathfinder ability to T1 and check if it needs rebalances | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Look at special attacks and make sure that all melee units who need it have it | 3 - Medium | 2 - Desired For Release | Unassigned | Unstarted
"Party Mode" for larger FFA games | 4 - Low | 3 - Post-Release | Unassigned | Unstarted
Brainstorm alternative winconditions like capture the hill | 4 - Low | 3 - Post-Release | Unassigned | Unstarted |  | Capture the flag? King of the hill?
Tau crisis suits withwider variety of weapons? Double chiaingun? | 5 - Trivial | 3 - Post-Release | Unassigned | Unstarted
Rites of exorcism deals more damage to Daemons | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Grenade abilities should not chase squads when selecting the squad | 3 - Medium | 2 - Desired For Release | Unassigned | Unstarted
"Regicide" achievement, first person to kill a commander | 3 - Medium | 2 - Desired For Release | Unassigned | Unstarted
Take another look at drop pod global for SM and give it fun bonuses | 4 - Low | 2 - Desired For Release | Ben | Unstarted |  | Deploy smoke on land in star around the drop pod, and heal nearby units
Take a look at penalising tyranids when they lose a structure | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Cryptek abilities for recycling bodies for scarab stuff? | 5 - Trivial | 4 - If we have time | Unassigned | Unstarted
Check if relocate can be used on squads? | 4 - Low | 2 - Desired For Release | Ben | Unstarted |  | Alternative TP for necron
Wings for Hive tyrant given on T2, not an addon | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Flayed ones are immortal when coming out of the ground, how to change this? | 4 - Low | 2 - Desired For Release | Ben | Unstarted

## Code
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Feral Boy Possession Global Ability | 2 - High | 1 - Required For Release | Ben | Unstarted | EBPs/SBPs
Chaos Preds Variants Possession | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Talos soul harvest ability | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Scavange ability system | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Special ability energy system | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Turret spawn global for Techmarine OM | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Turret spawn global for Enginseer | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Redo marauder bombing run ability for smoke | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Scarabs able to swap between air and ground | 3 - Medium | 2 - Desired For Release | Ben | Unstarted |  | Don't forget to remove the air scarabs
Rework living saint ability into code to avoid bugs | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Pray at icon idle behaviour | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Scout cultist spawn with prophet | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Tacs you build from orbital structure come as 8 models not 4 | 3 - Medium | 2 - Desired For Release | Ben | Unstarted |  | Maybe also spawn with sergeant and weapons
Rework drone harbinger so that its drones auto follow it and auto attack | 4 - Low | 2 - Desired For Release | Ben | Unstarted
List of units excluded from cover | 4 - Low | 1 - Required For Release | Ben | Unstarted
True random race scar | 5 - Trivial | 2 - Desired For Release | Ben | Waiting For Iteration |  | This is currently broken
Refactor to import scar files as variables instead of making them global | 5 - Trivial | 4 - If we have time | Ben | Unstarted
Look into Titanium wars level up UI | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Look into "ScatterFromSquad | 5 - Trivial | 2 - Desired For Release | Ben | Unstarted
Units with dozer blades able to destroy mines by running them over | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Possibly implement Die Last Leaders | 5 - Trivial | 4 - If we have time | Ben | Unstarted
Cosmetic music scar, should we keep it? If so finish it | 5 - Trivial | 4 - If we have time | Ben | Unstarted |  | Don't forget to add I.H and Nids here
To find exact locations of where entities die, use "spawn_on_death". Perhaps with a unique entity for each squad BP? | 4 - Low | 4 - If we have time | Ben | Unstarted
Add a generic class manager to run Updates | 3 - Medium | 2 - Desired For Release | Ben | Unstarted |  | Use a table
Torture amp causes units who die around it to generate souls | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Any units DE kills gives a small number of souls to the killer | 4 - Low | 2 - Desired For Release | Ben | Unstarted |  | Remove passive soul gen after 30 souls after this?
Experiment with transferring units to your allies | 4 - Low | 3 - Post-Release | Ben | Unstarted |  | Most interestingly rhinos
We need some way for of understanding combat in relation to entities (entity killing squad, or squad killing entity) | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Rework Tyranids auto builder to be more effective | 3 - Medium | 1 - Required For Release | Ben | Working On First Pass |  | World_GetSpawnablePosition
Importantly look over the Dev_SetupAutoConstructors in GlobalAbilities_Core as it might be depreciated. If it isn't depreciated, it needs to be redone as it's currently creating an auto builder just for player 1? | 3 - Medium | 1 - Required For Release | Ben | Unstarted |  | I need to really look into this auto builder carefully
Use Player_CanSeePosition to check if something is in fog of war, thus allowing you to stop globals being casted outside fow | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Remove cost for Hive tyrant weapon swap ability and make the hive tyrant pay with HP | 3 - Medium | 1 - Required For Release | Ben | Unstarted

## Audio
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Cultist worship audio | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Riders new voices | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Artillery spotter voice | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted

## Art
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
OM Leman Russ alt model from unification mod | 4 - Low | 1 - Required For Release | Ben | Unstarted
OM Assault Chimera model from unification mod | 4 - Low | 1 - Required For Release | Ben | Blocked | Check Cur Model
OM Check current assualt chimera to see if it supports autocannon | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Model for Champs Of Tzeentch | 3 - Medium | 2 - Desired For Release | Ben | Waiting For Iteration
Model for Noise Marines | 3 - Medium | 2 - Desired For Release | Ben | Waiting For Iteration
Model for Stalk Defiler | 3 - Medium | 2 - Desired For Release | Ben | Waiting For Iteration
Stalk defiler frenzy ability effects | 4 - Low | 2 - Desired For Release | Ben | Waiting For Iteration
Obliterator abilities effects | 4 - Low | 2 - Desired For Release | Ben | Waiting For Iteration
Chaos scout unit effect | 4 - Low | 1 - Required For Release | Ben | Unstarted
Simple model for scout unit trap | 4 - Low | 1 - Required For Release | Ben | Unstarted |  | Use a single mine from the mine fiels
Edit khorne zerks model so they get 2 axes in T3 | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Cultist worship effects | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Fire dragons alternative effect | 4 - Low | 1 - Required For Release | Ben | Unstarted
Alternative model for anti-infantry vyper | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Alternative model for eldar subcommander | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Riders Change to updated model | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Riders leader commissar model | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Leman Russ side arms lascannon bug fix | 4 - Low | 1 - Required For Release | Ben | Unstarted
Effects for ogryn abilities | 4 - Low | 1 - Required For Release | Ben | Unstarted
Sentinel and scout sentinel stomp animation | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Artillery spotters model | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Artillery spotter Icon | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Artillery spotter ability icons | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Scholars abilities need effects | 4 - Low | 1 - Required For Release | Ben | Unstarted
OM Icons pass | 4 - Low | 1 - Required For Release | Ben | Paused / On Hold
OM Effects general | 4 - Low | 1 - Required For Release | Ben | Unstarted
OM Tempest model alterations & new texture | 4 - Low | 2 - Desired For Release | Ben | Unstarted
OM Tempest psycannon effect | 4 - Low | 1 - Required For Release | Ben | Unstarted
OM grab updated acolyte model from unification and apply to bodyguards | 4 - Low | 1 - Required For Release | Ben | Unstarted
OM machine pit needs an altered model or texturing & make sure it doesn't go under ground | 4 - Low | 1 - Required For Release | Ben | Unstarted
Reclemator new model | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Possibly model for the Necron Tripods | 5 - Trivial | 4 - If we have time | Ben | Unstarted
Necron scout unit animation / firing tracer | 4 - Low | 1 - Required For Release | Ben | Unstarted
Pariah lord new / altered model | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Tomb spyder model that supports artillery | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Revisit sonic blaster effects | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Teleport animation for warboss | 4 - Low | 1 - Required For Release | Ben | Unstarted
Effect for slugga charge ability | 4 - Low | 1 - Required For Release | Ben | Unstarted
Ork burna boy nob model | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Stikkbombs model alterations to have bomb pack | 5 - Trivial | 2 - Desired For Release | Ben | Unstarted
Sisters dogmata and paragon suits models | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Novice sister icon ability needs 3D model | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Signposting and effects for cannonness witch hammer ability | 3 - Medium | 1 - Required For Release | Ben | Unstarted
SM sniper scout sniper ability effects | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Assault marines effect on landing instead of just a grenade explosion | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Rework apothecary to have bolt pistol | 5 - Trivial | 2 - Desired For Release | Omar | Ready For Approval
Firesight capping animation | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Consistency between the different healing / draining effects such as heal over time and instant heal | 4 - Low | 2 - Desired For Release | Ben | Unstarted
TC Snap shot animation | 3 - Medium | 2 - Desired For Release | Ben | Unstarted
Animations for special attacks on squads like raptors | 4 - Low | 1 - Required For Release | Unassigned | Unstarted

## Maps
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Decide which maps we wish to create TFE variants for | 4 - Low | 1 - Required For Release | All | Paused / On Hold
Air unit fix for FM TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for BM TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for BR TFE | 2 - High | 1 - Required For Release | Ben | Ready For Approval |  | I think this is already done..?
Air unit fix for EG TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for FC TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for MoM TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for SoE TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for TE TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Decide what we're doing with Sarajevo map | 5 - Trivial | 2 - Desired For Release | Unassigned | Paused / On Hold
TFE Variant of FM | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of BM | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of BR | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of EG | 4 - Low | 2 - Desired For Release | Ben | Working On First Pass |  | Improve pathing around mountains, check middle path on the opened up mountains, possibly adjust crit positions
TFE Variant of FC | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of MoM | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of SoE | 4 - Low | 1 - Required For Release | Ben | Waiting For Iteration |  | Widen pathing, fix stair collision, make impassable terrain clearer
TFE Variant of TE | 4 - Low | 2 - Desired For Release | Omar | Working On First Pass
Decide what new maps to make | 5 - Trivial | 2 - Desired For Release | All | Unstarted
BR Move Starting location to be slightly more forward | 3 - Medium | 1 - Required For Release | All | Unstarted
New Map: Long bridge | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
New Map: Poison Cover | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
New Map: Asymetrical Map | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
New Map: Height Cover Emphasis | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted |  | Rocky Valley? No Man's Land?
New Map: Open Map that does not guide the player | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted |  | This is pretty much EG though….

## QA
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
General multiplayer testing to see how abilities interact across factions | 3 - Medium | 1 - Required For Release | All | Unstarted
Look into every faction to test if they have the tier scaling for requisition | 3 - Medium | 1 - Required For Release | All | Unstarted
Killing LPs is currently counting as killing gens? | 5 - Trivial | 4 - If we have time | Ben | Unstarted |  | Achievement ssytesm

## Production
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Package the Objective Points mod stuff into the main mod | 5 - Trivial | 1 - Required For Release | Unassigned | Unstarted

## Macro
Priorities | Severities | Assignees | Statuses | Blocked By Example
1 - Urgent | 1 - Required For Release | Unassigned | Unstarted | Task
2 - High | 2 - Desired For Release | Ben | Paused / On Hold
3 - Medium | 3 - Post-Release | Omar | Blocked
4 - Low | 4 - If we have time | All | Working On First Pass
5 - Trivial |  |  | Waiting For Iteration
Iterating On
Done
Closed
Ready For Approval