## Design
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Skar Boy - EBPs, SBPs, Weapons | 2 - High | 1 - Required For Release | Omar | Working On First Pass
Ard Boy - EBPs, SBPs, Weapons | 2 - High | 1 - Required For Release | Omar | Working On First Pass
Ard Boy attach ranged weapon swapping | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Tyranid Scout Unit Design | 3 - Medium | 1 - Required For Release | All | Unstarted |  | We need to decide on a design for this unit then write up that design
Balancing Tau | 2 - High | 1 - Required For Release | All | Iterating On |  | This is blocking any upkeep
Finish initial rosta for Tyranids | 3 - Medium | 1 - Required For Release | All | Iterating On
Tau upkeep | 3 - Medium | 1 - Required For Release | All | Blocked | Balancing Tau
Sisters Faith Rework | 2 - High | 1 - Required For Release | All | Working On First Pass
Armour Resistance Rework | 4 - Low | 2 - Desired For Release | All | Working On First Pass
Implementing armour modifier to more places | 4 - Low | 2 - Desired For Release | All | Blocked | Armour Resistance Rework
Mass / Knockback Rework | 4 - Low | 2 - Desired For Release | All | Unstarted
OM add in leman variant unit | 3 - Medium | 1 - Required For Release | Omar | Unstarted
OM Assault Chim T3 weapon upgrade to assault cannon | 3 - Medium | 1 - Required For Release | Omar | Unstarted
Revisit current global abilities design | 4 - Low | 1 - Required For Release | All | Unstarted
Design for Tyranids global abilities | 4 - Low | 1 - Required For Release | All | Unstarted
Design for OM global abilities | 4 - Low | 1 - Required For Release | All | Unstarted
Design for Tau global abilities | 4 - Low | 1 - Required For Release | All | Unstarted
Decide how upkeep works in early game | 4 - Low | 1 - Required For Release | Omar | Unstarted |  | Do we want people to have a certain number of points / gens before we charge them?
Setup ability target filters for new armours | 1 - Urgent | 1 - Required For Release | Unassigned | Unstarted
Add piercings to abilities | 2 - High | 1 - Required For Release | Unassigned | Unstarted
Revisit BRV Design | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
BRV Faction | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
New (and multiplayer?) Campaign | 4 - Low | 3 - Post-Release | Unassigned | Unstarted
Tutorial/Demo level | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Revisit design for Alpha Legion subfaction | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Remove predator variants from machine pit | 3 - Medium | 1 - Required For Release | Unassigned | Blocked | Code system
Check if khorne zerks require more iteration | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Add havoc unit | 3 - Medium | 2 - Desired For Release | Omar | Working On First Pass
Iterate on Raven to make it a viable unit | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Ravage terror ability | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Pass on Talos | 3 - Medium | 1 - Required For Release | Ben | Unstarted | Souls Abil | Change cannibalize to ability, iterate on ranged weapon, pathing, check it's damage stats
Starting bike scavange ability rework | 3 - Medium | 1 - Required For Release | Omar | Unstarted | Scavange Abil
Look at rekindled rage global | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Soul Destruction Design | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted |  | Possibly do this as a zombie ability
Add the Incubus Combat squad | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Design a T3 ranged unit for DE | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Settle on dark reaper design | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Get rid of farseer variants | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Merge the eldar embolden abilities | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Cumulative squad cap for bonesingers | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Eldar holofields ability | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted | Energy System
Decide on wraithguard / wraithblade unit | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Harlequin kiss ability changed to timed not targeted | 3 - Medium | 1 - Required For Release | Unassigned | Unstarted
Revisit warlock sub-commander abilities | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Fire prism weapon swap ability | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Change guard assassin to research not addons | 4 - Low | 1 - Required For Release | Ben | Unstarted
Decide on Cln Brom | 5 - Trivial | 2 - Desired For Release | Unassigned | Unstarted
Earthshaker ability rework | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Revert change adding second turret (keep it in files) | 4 - Low | 1 - Required For Release | Unassigned | Unstarted
Rework hellhound T3 ability | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Rework marauder bomba | 2 - High | 1 - Required For Release | Ben | Unstarted |  | Bomb ability reworked into the combat and chang these bombs via weapon upgrades
Remove spotter vision ability | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Reworkand re-add secondary artillery abilty to a mixed use smoke | 3 - Medium | 1 - Required For Release | Ben | Unstarted

## Code
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Feral Boy Possession Global Ability | 2 - High | 1 - Required For Release | Ben | Unstarted | EBPs/SBPs
Chaos Preds Variants Possession | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Talos soul harvest ability | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Scavange ability system | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Special ability energy system | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Turret spawn global for Techmarine OM | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Turret spawn global for Enginseer | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Redo marauder bombing run ability for smoke | 4 - Low | 2 - Desired For Release | Ben | Unstarted

## Audio
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Cultist worship audio | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Riders new voices | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Artillery spotter voice | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted

## Art
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
OM Leman Russ alt model from unification mod | 4 - Low | 1 - Required For Release | Ben | Unstarted
OM Assault Chimera model from unification mod | 4 - Low | 1 - Required For Release | Ben | Blocked | Check Cur Model
OM Check current assualt chimera to see if it supports autocannon | 3 - Medium | 1 - Required For Release | Ben | Unstarted
Model for Champs Of Tzeentch | 3 - Medium | 2 - Desired For Release | Ben | Waiting For Iteration
Model for Noise Marines | 3 - Medium | 2 - Desired For Release | Ben | Waiting For Iteration
Model for Stalk Defiler | 3 - Medium | 2 - Desired For Release | Ben | Waiting For Iteration
Stalk defiler frenzy ability effects | 4 - Low | 2 - Desired For Release | Ben | Waiting For Iteration
Obliterator abilities effects | 4 - Low | 2 - Desired For Release | Ben | Waiting For Iteration
Chaos scout unit effect | 4 - Low | 1 - Required For Release | Ben | Unstarted
Simple model for scout unit trap | 4 - Low | 1 - Required For Release | Ben | Unstarted |  | Use a single mine from the mine fiels
Edit khorne zerks model so they get 2 axes in T3 | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Cultist worship effects | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Fire dragons alternative effect | 4 - Low | 1 - Required For Release | Ben | Unstarted
Alternative model for anti-infantry vyper | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Alternative model for eldar subcommander | 4 - Low | 2 - Desired For Release | Unassigned | Unstarted
Riders Change to updated model | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Riders leader commissar model | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Leman Russ side arms lascannon bug fix | 4 - Low | 1 - Required For Release | Ben | Unstarted
Effects for ogryn abilities | 4 - Low | 1 - Required For Release | Ben | Unstarted
Sentinel and scout sentinel stomp animation | 4 - Low | 2 - Desired For Release | Ben | Unstarted
Artillery spotters model | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Artillery spotter Icon | 4 - Low | 2 - Desired For Release | Omar | Unstarted
Artillery spotter ability icons | 4 - Low | 2 - Desired For Release | Ben | Unstarted

## Maps
Task | Priority | Severity | Assignee | Status | Blocked By | Notes
Decide which maps we wish to create TFE variants for | 4 - Low | 1 - Required For Release | All | Paused / On Hold
Air unit fix for FM TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for BM TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for BR TFE | 2 - High | 1 - Required For Release | Ben | Ready For Approval |  | I think this is already done..?
Air unit fix for EG TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for FC TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for MoM TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for SoE TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Air unit fix for TE TFE | 2 - High | 1 - Required For Release | Ben | Unstarted
Decide what we're doing with Sarajevo map | 5 - Trivial | 2 - Desired For Release | Unassigned | Paused / On Hold
TFE Variant of FM | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of BM | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of BR | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of EG | 4 - Low | 2 - Desired For Release | Ben | Working On First Pass
TFE Variant of FC | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of MoM | 4 - Low | 1 - Required For Release | Omar | Ready For Approval
TFE Variant of SoE | 4 - Low | 1 - Required For Release | Ben | Waiting For Iteration |  | Widen pathing, fix stair collision, make impassable terrain clearer
TFE Variant of TE | 4 - Low | 2 - Desired For Release | Omar | Working On First Pass
Decide what new maps to make | 5 - Trivial | 2 - Desired For Release | All | Unstarted

## QA
Task | Priority | Severity | Assignee | Status | Blocked By | Notes

## Production
Task | Priority | Severity | Assignee | Status | Blocked By | Notes

## Macro
Priorities | Severities | Assignees | Statuses | Blocked By Example
1 - Urgent | 1 - Required For Release | Unassigned | Unstarted | Task
2 - High | 2 - Desired For Release | Ben | Paused / On Hold
3 - Medium | 3 - Post-Release | Omar | Blocked
4 - Low | 4 - If we have time | All | Working On First Pass
5 - Trivial |  |  | Waiting For Iteration
Iterating On
Done
Closed
Ready For Approval